Crane Portfolio Intelligence

MVP Platform Proposal

KeyValue  ·  Crane Venture Partners

March 2026

Feature Spec  ·  Development Cost  ·  Infrastructure Estimates

1. What We’re Building

Crane Portfolio Intelligence is a purpose-built platform for Crane Venture Partners that consolidates portfolio data, automates monitoring workflows, and surfaces actionable insights across approximately 50–60 portfolio companies and 3 funds. The platform serves 20–30 internal users including partners, associates, and operations staff.

Today, Crane’s portfolio tracking relies on a fragmented workflow spanning spreadsheets, Dropbox folders, email threads, and the Gigs Excel tracker. This creates data silos, missed signals, and manual overhead that grows with every new investment. Crane replaces this entirely with a single, integrated intelligence layer.

The MVP connects 7 data sources — Attio (CRM), Dropbox (documents), Gmail (correspondence), Notion (internal notes), Granola (meeting transcripts), Specter (market intelligence), and AlphaSense (research analytics) — to power dashboards, alerts, board preparation, and portfolio review workflows.

MVP Principle: Ship a focused, functional product in 2–3 months. Every feature earns its place by solving a real workflow problem. Post-MVP features (semantic search, AI assistant, mobile app) are deliberately excluded to protect the timeline.

2. MVP Feature Scope

IN vs OUT

| Category | IN (MVP) | OUT (Post-MVP) |
| --- | --- | --- |
| Dashboard | Portfolio overview with KPIs, sparklines, fund selector | Customisable widget layouts |
| Command Center | Filterable company list with bulk actions | Saved custom views |
| Action Matrix | Urgency/impact grid for triage |  |
| Company Detail | Deep-dive with tabs: overview, financials, docs, contacts | AI-generated company summaries |
| Board Prep | Template-based board pack assembly | Auto-generated board narratives |
| Portfolio Review | Structured review workflows per company | Cross-portfolio benchmarking |
| Founder Verification | Standalone founder data-submission form | Multi-round verification flows |
| Alert Engine | 9 rule-based alert types with severity levels | ML-based anomaly detection |
| Connectors | 7 integrations (Attio, Dropbox, Gmail, Notion, Granola, Specter, AlphaSense) | Slack, Calendar, additional APIs |
| Export | Asset Metrix XLSX, LP Report PDF | Custom report builder |
| Auth & Users | Role-based access (Admin, Partner, Associate, Viewer) | SSO / SAML integration |
| Search | Keyword search across companies | Semantic / vector search |
| AI Features | Data extraction from documents | Conversational AI assistant |
| Mobile | Responsive web design | Native mobile app |
| Infrastructure | AWS-hosted, Crane-owned account | Multi-region / DR |

Feature Descriptions

Dashboard

Real-time portfolio overview displaying fund-level KPIs, sparkline performance charts, and a filterable company grid. Users select between Fund I, II, and III views, with at-a-glance health indicators for each company.

Portfolio Command Center

Central hub for day-to-day portfolio management. Presents a sortable, filterable list of all portfolio companies with inline status badges, last-contact dates, and bulk action controls for efficient triage.

Action Matrix

Two-dimensional urgency/impact grid that visually maps which companies need immediate attention. Companies are plotted by alert severity and business impact, (manullay for MVP)  enabling partners to prioritise effectively.

Company Detail

Deep-dive view for individual portfolio companies with tabbed navigation across overview, financials, documents, contacts, and activity timeline. Pulls consolidated data from all 7 connected sources into a single pane.

Board Prep (Skipped in MVP)

Template-driven workflow for assembling board meeting packs. Users select companies, choose a template, and the system pre-populates financial data, KPIs, and recent updates from connected sources. Export-ready output.

Portfolio Review

Structured review workflow for systematic assessment of portfolio companies. Supports scoring across multiple dimensions, reviewer assignments, comment threads, and approval flows. Designed around Crane’s quarterly review cadence.

Founder Verification Form

Standalone, externally accessible form that founders complete to submit or verify company data (revenue, headcount, runway, milestones). No Crane login required. Submissions flow directly into the company record and trigger update alerts.

Alert Engine ( Alert Rules can be changed)

Rule-based notification system that monitors portfolio data for actionable events. Supports 9 alert types with configurable severity levels:

| # | Alert Rule | Trigger Condition | Severity |
| --- | --- | --- | --- |
| 1 | Revenue Drop | MoM revenue decline > 15% | High |
| 2 | Runway Warning | Remaining runway < 6 months | Critical |
| 3 | KPI Miss | Key metric below target threshold | Medium |
| 4 | Stale Data | No data update in 30+ days | Low |
| 5 | Founder Non-Response | Verification form not completed in 14 days | Medium |
| 6 | Headcount Change | Headcount change > 20% in quarter | Medium |
| 7 | Follow-on Due | Time since last investment round > threshold | Low |
| 8 | Board Meeting Due | Next board meeting within 14 days, pack not started | High |
| 9 | Document Expiry | Key documents (SHA, cap table) older than 12 months | Medium |

Export & Reporting

Two primary export formats: Asset Metrix-compatible XLSX for LP reporting, and a branded LP Report PDF with fund performance summaries, company snapshots, and portfolio analytics. Both are generated on-demand with current data.

4. V1 Release — Minimum Usable Product

To get the Crane team productive as quickly as possible, the first usable release ships within 2–3 weeks of development start. V1 focuses on the single highest-value workflow: collecting validated data from founders and generating the Asset Metrix export. This gives the team a working tool for their next quarterly reporting cycle while the full MVP continues building in parallel.

V1 Compromise: Founder Forms First

Rather than attempting to ingest and parse unstructured data from board decks, emails, and transcripts from day one, V1 takes a pragmatic approach: send clean, pre-populated forms to founders for validation. Founders confirm, edit, or flag their data. This validated data flows directly into the Asset Metrix XLSX export. Automated extraction from unstructured sources layers in as the full MVP develops.

What Ships in V1 (Weeks 1–3)

| Component | What It Does |
| --- | --- |
| Founder Verification Form | Mobile-responsive form sent via secure token link. Pre-populated with last known values. Fields: Revenue, COGS, EBITDA, Cash Balance, Burn, ARR, Headcount (M/F/Ethnic Minority), Customers, Net Retention. No login required. Under 5 minutes to complete. |
| Data Capture & Storage | Founder submissions stored in the database with timestamps, edit tracking, and source attribution. Each field shows whether the founder confirmed, edited, or flagged it. |
| Asset Metrix XLSX Export | 3-sheet Excel export matching the fund administrator’s template: Company Commentary, Company Static, Company Periodic. Generated from founder-validated data. |
| Email Notifications | Automated emails to founders with form links. Reminder emails for non-responders after 7 and 14 days. Confirmation email on submission. |
| Basic Auth & Admin | Login for Crane team. Ability to send forms, view submissions, and trigger exports. |

What V1 Does NOT Include

• No dashboard, command center, or company detail pages (full MVP)

• No alert engine or board prep (full MVP)

• No data connectors beyond the founder form (Attio, Dropbox, Gmail etc. come in full MVP)

• No AI extraction or summarisation (full MVP)

V1 Timeline

| Week | What Gets Done |
| --- | --- |
| Week 1 | AWS setup, database schema, authentication, founder form UI (frontend + backend), email service (SES) |
| Week 2 | Form pre-population logic, submission flow, data validation, Asset Metrix XLSX generation engine |
| Week 3 | Email reminders, admin view for Crane team, QA, deploy to production |

V1 Outcome

The Crane team can send forms to all 50–60 portfolio company founders, collect validated quarterly data, and generate the Asset Metrix XLSX for their fund administrator — all within 3 weeks of project start. The full MVP (dashboard, alerts, reviews, board prep) continues building in parallel and ships at the end of the 2–3 month build.

4. Data Sources & Integration Costs

| # | Connector | Data Pulled | Sync Frequency | API Cost |
| --- | --- | --- | --- | --- |
| 1 | Attio (CRM) | Companies, contacts, deals, pipeline stages, custom fields | Real-time webhook + 15-min poll | ___ |
| 2 | Dropbox | Board packs, legal docs, financial reports (PDF/XLSX) | Webhook on file change | ___ |
| 3 | Gmail | Founder correspondence, meeting confirmations, LP emails | 5-minute poll via Gmail API | ___ |
| 4 | Notion | Internal company notes, meeting notes, investment memos | 15-minute poll | ___ |
| 5 | Granola | Meeting transcripts, action items, AI-generated summaries | Post-meeting webhook | ___ |
| 6 | Specter | Market intelligence, competitive signals, funding alerts | Daily batch sync | ___ |
| 7 | AlphaSense | Research reports, earnings transcripts, sector analytics | Daily batch sync | ___ |

Data Conflict Resolution Priority

When the same data point appears in multiple sources, the system applies the following priority hierarchy:

| Priority | Source | Rationale |
| --- | --- | --- |
| 1 (Highest) | Founder Verification Form | Direct from the company — most authoritative |
| 2 | Attio CRM | Manually curated by Crane team |
| 3 | Financial Documents (Dropbox) | Board-approved figures from uploaded documents |
| 4 | Granola Transcripts | Verbal confirmations from meetings, AI-extracted |
| 5 (Lowest) | Specter / AlphaSense | Third-party estimates — used as fallback only |

5. Infrastructure Details

All infrastructure runs on AWS, set up on Crane’s own AWS account by KeyValue DevOps engineers. On project completion, full ownership transfers to Crane with no vendor lock-in.

| Component | Service | Specification | Monthly Cost |
| --- | --- | --- | --- |
| Compute | EC2 / ECS Fargate | 2x t3.medium (API), 1x t3.small (workers) | ___ |
| Database | RDS PostgreSQL | db.t3.medium, 100GB, Multi-AZ standby | ___ |
| Cache | ElastiCache Redis | cache.t3.small, single node | ___ |
| File Storage | S3 | Standard tier, versioning enabled | ___ |
| CDN | CloudFront | Distribution for static assets and frontend | ___ |
| Email | SES | Transactional emails (alerts, invitations) | ___ |
| Monitoring | CloudWatch | Logs, metrics, alarms, dashboards | ___ |
| DNS | Route 53 | Hosted zone + health checks | ___ |

Infrastructure is provisioned via Infrastructure-as-Code (Terraform/CDK) for reproducibility. All secrets managed via AWS Secrets Manager. SSL certificates via AWS Certificate Manager.

6. Development Cost & Timeline

Team Composition

| Role | Duration | Est. Monthly Rate |
| --- | --- | --- |
| Senior Full-Stack Developer | 1-2 months | ___ |
| Frontend Developer | 1-2 months | ___ |
| AI/ML Engineer | 2-3 weeks | ___ |
| DevOps Engineer | 1 week | ___ |
| Product Manager (Ali) | 1-2 months | ___ |
| UI/UX Designer | 2 weeks | ___ |
| QA Tester | 2 weeks | ___ |

Man-Day Effort Breakdown

Estimated effort in man-days by discipline. These are parallel work streams — the 4 engineers (FE, BE, AI, DevOps) work simultaneously, so the calendar timeline is driven by the longest sequential path (back-end at 38 days ≈ 8 weeks).

| Category | FE Days | BE Days | AI Days | Total |
| --- | --- | --- | --- | --- |
| Setup & Infrastructure | 0.5 | 0.5 | 0 | 1 |
| Auth & User Management | 1 | 1.5 | 0 | 2.5 |
| Data Connectors (x7) | 0.5 | 8.5 | 5 | 13 |
| Dashboard | 4.25 | 2.25 | 0 | 6.5 |
| Command Center | 1.25 | 1.25 | 0 | 2.5 |
| Action Matrix | 1 | 1 | 0 | 2 |
| Company Detail | 5.75 | 5 | 0 | 10.75 |
| Portfolio Review | 5 | 6 | 2 | 13 |
| Board Prep (skipped) | 1.25 | 2 | 3 | 7.25 |
| Alert Engine | 1.5 | 4.5 | 0 | 5 |
| Export & Reporting | 1 | 2.5 | 0 | 4.5 |
| Settings & Admin | 1.75 | 1 | 0 | 2.75 |
| QA & Testing | 0 | 4 | 0 | 4 |
| TOTAL | 21.5 | 36 | 7 | 64.5 |

Development Cost Estimate

| Line Item | Cost Estimate |
| --- | --- |
| Core development team (Full-Stack + FE + DevOps) | ___ |
| AI/ML Engineer | ___ |
| PM, Design & Testing | ___ |
| Buffer (15%) | ___ |
| Total Development Cost | ___ |

Build Timeline

With 4 engineers working in parallel (frontend, back-end, AI, DevOps), the build completes in approximately 2–3 months. The critical path runs through back-end development at 38 man-days (≈8 weeks).

| Phase | Duration | What Gets Done |
| --- | --- | --- |
| Phase 1 — Foundation | Weeks 1–3 | AWS infrastructure setup, database schema, authentication & RBAC, Attio + Dropbox + Gmail connectors, core data models |
| Phase 2 — Core Platform | Weeks 4–7 | Dashboard, Command Center, Company Detail, Action Matrix, Board Prep, remaining connectors (Notion, Granola, Specter, AlphaSense), Alert Engine, AI extraction pipeline |
| Phase 3 — Workflows & Polish | Weeks 8–10 | Portfolio Review workflows, Founder Verification Portal, Asset Metrix XLSX export, LP Report PDF, AI summarisation, QA & regression testing, security review, soft launch |

7. Total Cost Summary

| Category | Low Estimate | High Estimate |
| --- | --- | --- |
| Development (one-time) | ___ | ___ |
| Monthly infrastructure | ___ | ___ |
| Annual infrastructure | ___ | ___ |
| Year-1 Total | ___ | ___ |

Excludes third-party data-source costs (Specter subscription, AlphaSense licence, etc.) which are billed directly to Crane by each vendor.

8. What Comes After MVP

The following capabilities are explicitly out of scope for the MVP but represent the natural product roadmap.

| Feature | Description | Added Cost |
| --- | --- | --- |
| Intelligence Hub | Centralised AI-powered insights dashboard with trend detection and anomaly alerts | ___ |
| Semantic Search | Vector-based search across all documents, notes, and transcripts | ___ |
| AI Assistant | Conversational interface for natural-language portfolio queries | ___ |
| Slack Integration | Real-time alert delivery and slash-command queries from Slack | ___ |
| Mobile App | Native iOS/Android app for on-the-go portfolio monitoring | ___ |
| Investor Portal | LP-facing read-only dashboard with fund performance and reporting | ___ |
| Advanced ESG | ESG scoring, carbon tracking, and diversity metrics per company | ___ |
| Cross-lingual OCR | Multi-language document parsing for international portfolio companies | ___ |

9. Key Risks

| # | Risk | Impact | Likelihood | Mitigation |
| --- | --- | --- | --- | --- |
| 1 | API rate limits or downtime on third-party services | Data freshness degrades | Medium | Implement retry logic, circuit breakers, and cached fallback data |
| 2 | Data quality inconsistencies across sources | Incorrect portfolio metrics | High | Conflict resolution hierarchy + data validation rules + manual override |
| 3 | Scope creep during build | Timeline slips past June | Medium | Strict MVP boundary enforced by PM; change requests go to post-MVP backlog |
| 4 | Founder verification adoption | Incomplete company data | Medium | Simple, mobile-friendly form; automated reminders; fallback to manual entry |
| 5 | AWS cost overrun | Budget exceeded | Low | Cost alerts, reserved instances, right-sizing reviews at Week 4 and Week 8 |
| 6 | Key person dependency | Delivery stalls if team member unavailable | Low | Cross-training, documentation, and pair programming practices |
| 7 | Security / data breach | Reputational and regulatory exposure | Low | Encryption at rest and in transit, RBAC, audit logging, pen-test before launch |

10. Assumptions

This proposal is based on the following assumptions. Material changes to these may affect scope, timeline, or cost.

- Portfolio size of approximately 50–60 companies across 3 funds

- 20–30 internal users (partners, associates, operations, finance)

- AWS-only infrastructure, hosted on Crane’s own AWS account

- 7 data connectors only (Attio, Dropbox, Gmail, Notion, Granola, Specter, AlphaSense) — no fund accounting integration

- Crane provides timely API credentials and sandbox access for all 7 data sources

- No single sign-on (SSO/SAML) required for MVP — email/password authentication with RBAC

- Design assets and brand guidelines provided by Crane within Week 1

- One round of UAT feedback incorporated before launch; further iterations are post-MVP

- KeyValue DevOps team sets up and manages infrastructure during build; ownership transfers to Crane on completion

- Third-party data costs (Specter, AlphaSense subscriptions) are borne by Crane directly

11. Agreement & Working Terms

Scope

This proposal covers the design, development, and deployment of the Crane Portfolio Intelligence MVP as described in Sections 1–6. Any features or integrations not explicitly listed in the “IN” column of Section 2 are out of scope for this engagement.

Methodology

Development follows an agile methodology with 2-week sprints. Each sprint includes planning, development, review, and retrospective. Bi-weekly demos are scheduled with the Crane team to review progress and gather feedback.

Scope Changes

Any changes to the agreed scope will be documented as a formal change request. Change requests include: description of the change, impact on timeline, impact on cost, and approval from both parties before work begins. The 15% buffer in the cost estimate covers minor adjustments and unforeseen complexity, not new features.

Timely Availability

The Crane team commits to timely availability for: sprint reviews and demos (bi-weekly), decision-making on open questions (within 48 hours), providing access to third-party services and API credentials, reviewing and approving deliverables at each milestone, and providing the Asset Metrix XLSX template.

Deliverables

At project completion, KeyValue delivers:

- Fully deployed MVP platform on Crane’s AWS account

- Source code in a private Git repository (transferred to Crane)

- Technical documentation (architecture, API reference, deployment guide)

- Admin guide and user onboarding materials

12. Next Steps

To proceed, we recommend the following actions:

| # | Action | Owner | Target Date |
| --- | --- | --- | --- |
| 1 | Review and approve this MVP proposal | Crane Partners |  |
| 2 | Sign statement of work and process upfront payment | Crane + KeyValue |  |
| 3 | Provide API credentials for all 7 data sources | Crane Ops |  |
| 4 | Provide brand guidelines and design assets | Crane |  |
| 5 | Kick-off meeting and sprint planning | KeyValue PM |  |
| 6 | AWS account setup and infrastructure provisioning | KeyValue DevOps |  |
| 7 | Phase 1 delivery checkpoint | KeyValue |  |
| 8 | Phase 2 delivery checkpoint | KeyValue |  |
| 9 | MVP launch and UAT | All |  |